## Requirement
No. | Description | Type | Priority | Cover by
1 | Main board is moved from enclosure’s window to piggy-back with Relay boards. Connectors should be changed accordingly. | New | High
2 | Add 1 RS485 connector | New | High | Project Plan'!B10
3 | Add 1 RTC module | New | High | Project Plan'!B11
4 | All input/output should be placed according to Vu's 3D design. Suggestions are welcome as well. If possible, Tri Viet power board should be placed in the same surface as relay board. | Improve | Normal
5 | Changed 6 small relays to Solid state relay if possible (design/BoM/price suggestion first) NC when power is cut off or the device is shutted down AC outputs: 220VAC/5kW 6 DC outputs: 48VDC/100W | Improve | Low | Project Plan'!B14
6 | Suggest connector e.g. power connector from power board, 1wire, rs485/232 if it's better | Improve | Low
7 | RS422 connection is timed out randomly (some board have 1, 2 message before timed out; some 10, 20; some 100, 200…). Review RS422 board and RS422 in Main board is needed to see if the connection time out is caused by hardware. | Existing Bug | Highest
8 | Power connector should be improved to: 1. In Tri Viet board - 48VDC input connector: http://thegioiic.com/products/hb9500-2p 2. In Tri Viet board - 12V/5V output connector: http://thegioiic.com/products/5557-power-connector-wire 3. In Relay board - 12V/5V input connector: Same as No.2 | Improve | High
9 | Reverse engineer Tri Viet power board if possible and cheaper than buying from Tri Viet. Pulse transformer can be bought from Tri Viet.
10 | Add 2 connectors: 12V and 5V output (for external sensor usage) to Relay board (near the inputs of Burglar, Fire, Smoke, Water…) | New | Normal
11 | Review RS422 board to see if connection time
12

## Project Plan
PIF - ACDT SNMP CHANGES LOG
|  | Owner | ACDT | Project code: | ACDT-AA-01
|  | Date | 08/04/2016 | Revision: | 01
Date | Changes ID | Categories | Details | Confirm | Remark
2016-04-04 | 1 | Main Board | Thay đổi kích thước board, việc tận dụng relay làm đế giữ board sẽ gây nhiễu main board khi relay đóng cắt. | OK
2016-04-04 | 2 | Main Board | Board main khi lật ngược cắm header sẽ vướng cổng ethernet, jack 5v => cắt board tại vị trí đó (vị trí cắt được dựa trên tài liệu REVC của board BBB) | OK
2016-04-04 | 3 | Main Board | Đặt board Main cách relays 1 chút để hạn chế nhiễu | OK
2016-04-04 | 4 | Main Board | Thêm module RS485 | OK | Xem sheet #4
2016-04-04 | 5 | Main Board | Thêm module RTC BQ32000 | OK | Xem sheet #4
2016-04-05 | 6 | Relay Board | Thay schematic phần kích relay, thêm linh kiện bảo vệ (cách kích relay cũ trên board về mặt kĩ thuật chưa đúng, gây tác động không tốt đến board điều khiển). @a Phương xem sheet #6 giúp em Có nên dùng LED để báo trạng thái relay không? [08Apr] LED vẫn cần để thuận tiện nhân viên không cần kiến thức về relay vẫn lắp và vận hành được, Phương suggest schematics khác cũng được. |  | Xem sheet #6
2016-04-05 | 7 | Relay Board | Thay đổi lại cách layout board relay (cách đi layout cũ chưa đúng với mục đích cách ly khi sử dụng opto, nhiễu) | OK
2016-04-05 | 8 | Relay Board | Sử dụng relay SSR thay cho các relay nhỏ https://www.digikey.com/product-detail/en/ixys-integrated-circuits-division/CPC1916Y/CLA209-ND/654909 @A Phương or Vũ cho em biết các SSR đóng tải loại gì (AC or DC, bao nhiêu Volt?) [08Apr] Cái SSR này phụ thuộc vào lại tải nữa hả Phương? Tại anh tính làm nó universal và có thể áp dụng được cho SmartOutlet (đóng mở nguồn các thiết bị điện trong nhà: đèn, quạt, máy lạnh...) |  | Xem sheet #8
2016-04-06 | 9 | Main Board | Thay dổi giá trị trở Pullup/Pulldown theo recommend từ chuẩn EIA-422 | OK | Xem sheet #9
2016-04-06 | 10 | Main Board | Sử dụng MAX3485 thay cho SP3485 | OK
2016-04-06 | 11 | Main Board | RS422: Trở nối chân A kéo lên, chân B kéo xuống (board cũ ngược lại) Đối với đường truyền serial người ta thường reconmend như vậy. | OK | Xem sheet #9
2016-04-06 | 12 | LCD Board | chỉnh vị trí 4 nút bấm lại 1 chút để khớp màn hình (design cũ xếp hơi lệch) | OK | Xem sheet #12 - not add yet

## #6
LED D12: Khi kích đóng relay thì đèn LED này sáng --> dễ debug.
Anh Phương giúp em kiểm tra lại sự cần thiết của LED này, nếu không cần thiết thì bỏ đi.

## Legacy
Bug Type | New | Improve | Existing Bug
Priority | Highest | High | Normal | Low | Lowest